## Project Planner
Airbnb Project Gantt Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
#001 Gantt Chart | 1 | 5 | 1 | 5 | 100%
#002 Preparation for Project Plan | 5 | 6 | 5 | 6 | 100%
#003 Defining the scope | 6 | 7 | 6 | 8 | 100%
#004 Breaking down the structure of the project | 7 | 9 | 8 | 9 | 100%
#005 Acitivy Definition and Estimation | 9 | 10 | 9 | 11 | 100%
#006 Preparation for Software Design Document | 10 | 12 | 11 | 13 | 100%
#007 Analysing the requirements for user and software | 12 | 14 | 13 | 16 | 100%
#008 Making the use cases and use case diagram | 14 | 16 | 16 | 18 | 100%
#009 Analysing about the Software Design and System Components | 16 | 18 | 18 | 21 | 100%
#010 User Interface Design- Structural and Visual | 18 | 21 | 21 | 24 | 100%
#011 Including the Gantt Chart in the Project Plan Document | 21 | 21 | 24 | 24 | 100%
#012 Downloading git_log.txt | 21 | 22 | 24 | 24 | 100%
#013 Code for Data Analysis | 22 | 26 |  |  | 0%
#014 Preparing the User Manual.docx | 26 | 28 |  |  | 0%
#015 Creating Software Testing Report.docx | 28 | 31 |  |  | 0%
#016 Preparing the Executive Summary.docx | 31 | 33 |  |  | 0%
Activity 17 |  |  |  |  | 0%
Activity 18 |  |  |  |  | 0%
Activity 19 |  |  |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%